## Yearly plan
Quarter | From | To | Goal | Difficulty | Status
Quarter 1 | 2024-01-01 | 2024-03-31 | Improve Coding skill | Medium | Done
Quarter 2 | 2024-04-01 | 2024-06-30 | Learn new sport | Easy | In progress
Quarter 3 | 2024-07-01 | 2024-09-30 | Build and deploy a python web project | Hard | To Do
Quarter 4 | 2024-10-01 | 2024-12-31 | Gain Azure devops certification | Medium | Done
Goals
Quarter 1: Improve Coding skill
Complete udemy code for Java
Complete udemy code for Springboot
Quarter 2: Learn new sport
Learn to play pickle ball
Quarter 3: Build and deploy a python web project
Prepare and build python web project with scikit learn and flask
Quarter 4: Gain Azure devops certification
Take and passAZ-400 certification

## Quarter plan
Year plan 2024
Quarter plan 3
Project name |  | PM | Start Date | End date
Udacity project |  | Anhdv29 | 2024-07-01 | 2024-09-20
Week | From | To | Sprint | Backend | Frontend | Difficulty | Status
Week 1 | 2024-07-01 | 2024-07-05 | Sprint 1 | Set up Azure cloud Shell | Build Core project for Frontend | Medium | Done
Week 2 | 2024-07-08 | 2024-07-12 |  | Set up Azure Devops Pipeline | Build Frontend Project | Easy | In progress
Week 3 | 2024-07-15 | 2024-07-19 | Sprint 2 | Build Backend Project | Build Frontend Project | Hard | To Do
Week 4 | 2024-07-22 | 2024-07-26 |  | Build Backend Project | Build pipeline for Frontend System | Medium | Done
Week 5 | 2024-07-29 | 2024-08-02 | Sprint 3 | Setup K8s Environment | Integrate with Backend System | Easy | In progress
Week 6 | 2024-08-05 | 2024-08-09 |  | Setup security for K8s | Review Code for Frontend Project | Hard | To Do
Week 7 | 2024-08-12 | 2024-08-16 | Sprint 4 | Setup security for Backend Project | Setup security for Frontend Project | Medium | Done
Week 8 | 2024-08-19 | 2024-08-23 |  | Test Backend system in Local environment | Test Frontend system in Local environment | Easy | In progress
Week 9 | 2024-08-26 | 2024-08-30 | Sprint 5 | Test Backend system in Dev environment | Test Frontend system in Dev environment | Hard | To Do
Week 10 | 2024-09-02 | 2024-09-06 |  | Test Backend system in Test environment | Test Frontend system in Test environment | Medium | Done
Week 11 | 2024-09-09 | 2024-09-13 | Sprint 6 | Test Backend system in QA environment | Test Frontend system in QA environment | Easy | In progress
Week 12 | 2024-09-16 | 2024-09-20 |  | Deploy Backend System to production | Deploy Backend System to production | Hard | To Do
Goals
Complete Backend System setup
Build CICD Pipeline
Complete Frontend Project
Deploy Frontend to K8s